## Summary
Sri Jayam Printers ERP — Billing App QA Test Report
Live: https://sri-jayam-erp-frontend-745036261829.asia-south1.run.app ¦ Local QA + cloud deploy verification: 2026-08-22 ¦ Tester: Claude (QA / end-user)
32 | 26 | 6 | 6
Total Test Cases | Passed (no issue) | Issues Found | Issues Fixed & Re-verified
Result
All 6 issues found during this pass were fixed and re-verified live — 2 application bugs (a product-picker row limit, and optional date fields rejected as invalid) that showed up identically in 3 separate forms, plus 2 deployment-only bugs that only a fresh-database, production-build deploy could have exposed. Nothing was left open.

## Test Cases
Test ID | Area | Test Case | Steps Performed | Expected Result | Actual Result | Status | Severity | Fix Status | Resolution
B1 | Auth / RBAC | Admin login | Log in as admin@srijayam.com | Dashboard loads, full sidebar visible | Full sidebar (13 items) shown, dashboard data loads correctly | PASS | - | - | -
B2 | Auth / RBAC | Counter role — nav gating | Create a Counter-role test user, log in as them | Only Counter-relevant items in sidebar (no Pricing Setup, Purchases, Cash Ledger, Users, Masters) | Sidebar correctly shows 8 items, matching documented Counter scope | PASS | - | - | -
B3 | Auth / RBAC | Counter role — blocked page via direct URL | As Counter, navigate directly to /users and /cash-ledger | Clean "Not authorized" message, no data leak | Both routes show "Your role (counter) doesn't have access to this page" with no data rendered | PASS | - | - | -
B4 | Auth / RBAC | Counter role — API-level enforcement | Call cash-ledger/summary, users/, purchases/ (POST), invoices DELETE directly with Counter's token | 403 on all admin/accounts-only actions; read-only purchases list allowed per spec | cash-ledger 403, users 403, purchase create 403, invoice delete 403, purchase list 200 (reads open to any staff, as designed) | PASS | - | - | -
B5 | Auth / RBAC | Production role — nav + API | Create Production test user, repeat nav + API checks | Same restricted set as Counter, plus job-card delete blocked | Nav matches Counter; job-card delete correctly 403 | PASS | - | - | -
B6 | Auth / RBAC | Accounts role — nav + API | Create Accounts test user, repeat nav + API checks | Purchases, Inventory, Cash Ledger visible and writable; Users still blocked | cash-ledger 200, purchases 200, inventory 200, users 403, invoice/job-card delete 403 — exactly matches documented design | PASS | - | - | -
B7 | Customers | Add customer | Create a new customer with name, phone, email | Customer saved and appears in list | Customer created and listed correctly | PASS | - | - | -
B8 | Customers | Search customers | Search by partial name/phone in a picker field | Matching customers returned | Search-mode Autocomplete returns correct matches | PASS | - | - | -
B9 | Products | Product catalog loads | Open Products page after seeding all 14 categories | Full catalog visible | 123 products across 14 categories listed correctly | PASS | - | - | -
B10 | Products | Product picker missing items past 100 | Search for "Xerox" in the Quotation/Billing Counter product picker after full catalog seeded | Xerox / Photocopy appears in results | Not found — GET /products/ silently capped at limit=100; Xerox (seeded last) fell outside it with no error shown | FAIL | High | FIXED | Raised default limit on /products/ and /product-categories/ from 100 to 2000. Verified all 123 products now return and are searchable.
B11 | Quotations | Create matrix-priced quotation | Add Xerox/Photocopy, pick Paper Size/Colour/Print Side, qty 10 | Correct unit price × qty, 18% GST applied, grand total correct | ₹10.00 unit × 10 = ₹100.00 subtotal, ₹18.00 tax, ₹118.00 grand total — verified against Price Matrix | PASS | - | - | -
B12 | Quotations | Optional Delivery Date left blank | Create a quotation leaving Delivery Date/Time empty (fields carry no asterisk) | Quotation saves successfully | 422 "Input should be a valid date or datetime, input is too short" — frontend sent "" instead of omitting the field | FAIL | High | FIXED | QuotationCreate.tsx now normalizes empty date/time strings to undefined before submit. Re-tested: quotation saves cleanly with blank dates.
B13 | Quotations | Convert to job cards | Convert a draft quotation | Status becomes "Converted", one job card per line item created | Confirmed — job card(s) created with correct product/customer/quantity | PASS | - | - | -
B14 | Job Cards | Job card fields correct | Inspect a job card created from conversion | Customer, product, status=pending all correct | All fields correct, status defaulted to pending | PASS | - | - | -
B15 | Job Cards | Assign dialog with blank Delivery Date | Open a job card's Assign dialog, save without touching Delivery Date | Saves successfully (field is optional) | Same empty-string-vs-null bug as B12 — PUT /job-cards/{id} rejected "" as an invalid date | FAIL | High | FIXED | JobCards.tsx assign form now normalizes the same way. Re-tested: save succeeds with delivery_date left blank.
B16 | Invoices | Create invoice from quotation | Create Invoice on a converted quotation | Invoice generated with matching totals, status Unpaid | INV-#### created, totals match the quotation exactly, status Unpaid | PASS | - | - | -
B17 | Invoices | Record partial payment | Record a payment less than the grand total | Status becomes Partially Paid, balance recalculated | Paid/Balance amounts and status updated correctly | PASS | - | - | -
B18 | Invoices | PDF export — A4 | Download invoice PDF, format=a4 | Valid PDF, A4 layout | 200 OK, application/pdf, correct layout | PASS | - | - | -
B19 | Invoices | PDF export — 58mm thermal | Download invoice PDF, format=thermal_58 | Valid PDF sized for a 58mm roll | 200 OK, correctly narrow receipt layout | PASS | - | - | -
B20 | Invoices | PDF export — 80mm thermal | Download invoice PDF, format=thermal_80 | Valid PDF sized for an 80mm roll | 200 OK, correctly sized receipt layout | PASS | - | - | -
B21 | Billing Counter | Live price preview | Add a line item, fill required attributes and quantity on the new counter screen | Rate and Amount appear live, before saving anything | New POST /quotations/preview endpoint returns correct unit_price/total_price with no DB writes; UI updates within ~300ms of the last change | PASS | - | - | -
B22 | Billing Counter | Cash tendered / change due | Click quick-cash buttons, compare to Net Amount | Change Due = tendered − grand total | ₹100 tendered against a ₹59 bill correctly showed ₹41 change due | PASS | - | - | -
B23 | Billing Counter | Save & Print — full chain | Fill a full bill and hit Save & Print | Customer, quotation, job card, and invoice all created; thermal PDF opens for printing; screen resets for the next bill | Full chain confirmed via network trace (customer 201 → quotation 200 → convert 200 → invoice 201 → PDF fetch 200); success banner shown; form cleared | PASS | - | - | -
B24 | Purchases | Add vendor | Create a new vendor | Vendor saved and listed | Vendor created correctly | PASS | - | - | -
B25 | Purchases | Record purchase — stock increments | Create a purchase of 20 reams against an inventory item starting at 5 | Inventory current_qty increases by the purchased quantity automatically | Stock correctly moved from 5 → 25 with no manual step | PASS | - | - | -
B26 | Inventory | Low-stock flagging | View an item at/below its reorder threshold | Flagged "Low Stock" with a page banner | Correctly flagged; banner disappeared once the purchase above brought it above threshold | PASS | - | - | -
B27 | Cash Ledger | Record cash transaction | Record a Receipt of ₹500 | Cash in Hand increases by ₹500 | Summary recalculated correctly | PASS | - | - | -
B28 | Cash Ledger | Add cheque with blank optional dates | Add a cheque, leaving Cheque Date and Deposit Date blank (both optional) | Cheque saves successfully | Same empty-string-vs-null bug as B12/B15 — 422 on both optional date fields | FAIL | Medium | FIXED | CashLedger.tsx cheque form now normalizes both date fields the same way. Re-tested: saves cleanly with blank dates, shown as "-" in the list.
B29 | Cash Ledger | Cheque list + status | View Cheques tab, change a cheque's status | List and inline status dropdown work correctly | Confirmed | PASS | - | - | -
B30 | Reports | Sales report + Excel export | View This Month's sales, download Excel | Correct totals shown; valid .xlsx download | Totals matched invoice data; export returned valid spreadsheetml content | PASS | - | - | -
B31 | Deployment | Fresh-database migration replay | Run `alembic upgrade head` against a brand-new Cloud SQL database (first time ever replayed end-to-end) | All migrations apply cleanly | relation "customers" already exists — a later migration (1bab961191b5) had a stale duplicate create_table('customers',...) left over from before an earlier migration was fixed to create it | FAIL | Critical | FIXED | Made the duplicate migration a no-op (kept in the chain so later revision IDs don't shift). Re-ran cleanly against a fresh database; verified via login + full CRUD.
B32 | Deployment | Frontend pointed at a non-local backend | Build frontend for production, check API base URL | Configurable via environment, not hardcoded | baseURL was hardcoded to http://localhost:8000/api/v1 with no override — would have made any non-local deployment silently fail | FAIL | Critical | FIXED | Switched to VITE_API_URL (same pattern as the printing website), with .env.production pointing at the deployed backend. Verified the built bundle references the correct URL and the live app connects successfully.